## Slide 1
EPMO Intelligence
Portfolio Performance Report
May 17, 2026
C O N F I D E N T I A L

## Slide 2
Executive Summary
20
Total Projects
SAR 16.5M
Total Budget
3
Critical
60%
Health
Status Breakdown
On Track: 10 projects (50%)
Delayed: 5 projects (25%)
Critical: 3 projects (15%)
Completed: 2 projects (10%)
Key Metrics
Avg Completion: 62%
Budget Utilization: 65%
Budget Execution: 87.8%
Milestones: 78.5%
Resources: 84.5%
Satisfaction: 3.9/5.0

## Slide 3
Portfolio Analytics
Status Distribution
On Track
10 (50%)
Delayed
5 (25%)
Critical
3 (15%)
Completed
2 (10%)
Budget by Department
Information Tech..
8780K
Finance & Budget
1660K
Procurement
1260K
Operations
1200K
Digital Transfor..
1170K
Strategy & Plann..
800K
Total Budget: SAR 16.5M | Spent: SAR 10.8M (65%)

## Slide 4
Critical & Delayed Projects
Projects requiring immediate leadership attention
Project | Department | Status | Budget | Spent% | Done% | Risk
ERP Upgrade | Information Te | Delayed | 2800K | 75% | 72% | High
Cybersecurity Enhancem | Information Te | Critical | 1500K | 95% | 90% | High
Smart Building Managem | Operations | Critical | 1200K | 96% | 88% | High
Treasury Management Sy | Finance & Budg | Delayed | 890K | 80% | 75% | High
Vendor Management Port | Procurement | Critical | 580K | 95% | 85% | High
Data Governance Framew | Information Te | Delayed | 480K | 80% | 65% | High
SOX Compliance Automat | Internal Audit | Delayed | 460K | 80% | 70% | High
Regulatory Compliance | Legal Affairs | Delayed | 350K | 80% | 70% | High

## Slide 5
KPI Performance
✓
Budget Execution
Target: 85%
87.8%
✗
Milestone Achievement
Target: 85%
78.5%
✓
Resource Utilization
Target: 80%
84.5%
✗
Satisfaction Score
Target: 4.0/5
3.9/5
✗
Avg Escalations
Target: 2.0 max
2.2

## Slide 6
Recommendations & Next Steps
Immediate Action Required
HIGH
3 critical projects need steering committee review. Cybersecurity and Vendor Mgmt highest priority.
Recovery Plans for Delayed Projects
HIGH
5 delayed projects require recovery plans. ERP Upgrade and Treasury Mgmt largest exposure.
Budget Reallocation Review
MEDIUM
Utilization at 65%. 3 projects over 80% spent.
Stakeholder Engagement
MEDIUM
Satisfaction 3.9/5.0, 2.2 escalations avg. Recommend communication plan.
Generated by ARRC EPMO Intelligence Platform | May 17, 2026 | Confidential